## Sheet1
Epic Creation:
Epic ID | Epic Name | Description
E1 | Authentication & Login | Implement user authentication and login system.
E2 | Account Management | Develop features for managing user accounts.
E3 | Fund Transfer | Implement secure and efficient fund transfers.
E4 | Transaction History | Display a comprehensive transaction history.
E5 | Payment Options | Integrate various payment options for users.
User Stories Creation:
User Story ID | Epic ID | User Story Name | Description
US1 | E1 | User Authentication | As a user, I want to securely log in to my account.
US2 | E1 | Login History | As a user, I want to view my login history.
US3 | E2 | Profile Management | As a user, I want to update my profile information.
US4 | E3 | Fund Transfer Initiation | As a user, I want to initiate a fund transfer.
US5 | E3 | Fund Transfer Confirmation | As a user, I want to confirm and review fund transfers.
US6 | E4 | View Transaction History | As a user, I want to view a detailed transaction history.
US7 | E5 | Payment Options Integration | As a user, I want to choose from various payment options.
Backlog Creation:
Task ID | User Story ID | Task Description
T1 | US1 | Implement user authentication mechanism.
T2 | US2 | Develop a feature to track and display login history.
T3 | US3 | Create functionality for profile information update.
T4 | US4 | Implement the initiation process for fund transfers.
T5 | US5 | Develop the confirmation process for fund transfers.
T6 | US6 | Design a comprehensive transaction history display.
T7 | US7 | Integrate various payment options into the system.
Sprint Planning:
Sprint ID | Sprint Name | Sprint Duration | Assigned Tasks | Priority
SP1 | Initial Setup | 2 weeks | T1, T2 | High
SP2 | User Accounts | 3 weeks | T3, T4 | High
SP3 | Fund Transfer | 3 weeks | T5, T6 | High
SP4 | Payment Options | 2 weeks | T7 | High